## Cover Page (hidden)
Author
Reviewer
Approver
Approved on
Test Estimation - Template Version 1.0 ITAS - Testing Services
Estimation Template
Client Name
Project Name

## Guidelines to Use
Guidelines to Use this template
| Sheets to be used |  | Sheets for Reference | Details
1 | Summary |  | Effort Definition | This sheet gives the details of effort breakdown for each of the activities based on their complexities, based on stream
2 | Effort Breakdown |  | Complexity Guide | This sheet gives the details of complexities definition
3 | Assumptions
Guidelines to use
1 | Use the Effort Breakdown sheet first
Enter the requirement name and its details and select the appropriate complexity of the requirement
The effort breakdown for the requirement automatically fills up
Continue the complexity selection for the remaining requirements
If needed, please insert rows inbetween, Do not copy the formulae
2 | Once all requirements estimation is completed, now use the Summary sheet
All columns in Blue is read-only and should not be updated
Column C would give the total effort needed phase wise, for the entire requirements
Use Column C to indicate whether the phase is in scope or not
Use column D to enter your analysis of how much effort would be needed for the phase. It can be same as Column C or different
If the effort values in column D is different to that of column C, enter the reasons for the same
3 | List down all assumptions made during estimation, in the Assumptions sheet
4 | This completes the estimation process
5 | Get the estimation reviewed by Delivery Manager
6 | Use this estimated effort for creating your schedule (mpp)

## 01 Effort Breakdown
S.No. | Requirment/BRD/Module/StoryCard/Test Case | Description ( Valiations involved) | Complexity | Complexity Point | Requirement Analysis | Test Design | Test Execution | Defect Management | Regression Testing(Cycle 1) | Review | Rework | Reporting/Tracking/Other Activities | Total Test Effort ( in Person Hours)
| Example 1 |  | Simple | 3 | 0.5 | 1 | 1 | 0.25 | 0.5 | 0.25 | 0.25 | 7 | 10.75
| Example 2 |  | Simple | 3 | 0.5 | 1 | 1 | 0.25 | 0.5 | 0.25 | 0.25 | 7 | 10.75
| Example 3 |  | Medium | 5 | 1 | 3 | 4 | 1.5 | 3 | 0.25 | 0.25 | 0.25 | 13.25
| Example 4 |  | Complex | 8 | 2 | 5 | 8 | 2 | 10 | 0.25 | 0.5 | 0.25 | 28
| Example 5 |  | Complex | 8 | 2 | 5 | 8 | 2 | 10 | 0.25 | 0.5 | 0.25 | 28
| Example 6 |  | Complex | 8 | 2 | 5 | 8 | 2 | 10 | 0.25 | 0.5 | 0.25 | 28
| Example 7 |  | Very Simple | 1 | 0.25 | 0.25 | 1 | 0.25 | 0.5 | 0 | 0 | 0.25 | 2.5
| Example 8 |  | Medium | 5 | 1 | 3 | 4 | 1.5 | 3 | 0.25 | 0.25 | 0.25 | 13.25
| Example 9 | [11 empty] | 0
| Example 10 | [11 empty] | 0
| Example 11 | [11 empty] | 0
| Example 12 | [11 empty] | 0
| Example 13 | [11 empty] | 0
| Example 14 |  | Medium | 5 | 1 | 3 | 4 | 1.5 | 3 | 0.25 | 0.25 | 0.25 | 13.25
| Example 15 | [11 empty] | 0
| Example 16 | [11 empty] | 0
| Example 17 | [11 empty] | 0
| Example 18 | [11 empty] | 0
| Example 19 | [11 empty] | 0
| Example 20 |  | Medium | 5 | 1 | 3 | 4 | 1.5 | 3 | 0.25 | 0.25 | 0.25 | 13.25
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total |  |  |  | 51 | 11.25 | 29.25 | 43 | 12.75 | 43.5 | 2.25 | 3 | 16 | 161
**Only cells in Blue should be edited
** Please use the Complexity Column field list to select the complexity of the requirment
** The complexity of the requirment can be used by using the "Complexity Guide" worksheet Complexity Calculator
** Please Ensure that the lines are inserted as and when the line items need to be included.
** User discretion can be used in defining the complexities. Hiint : Further break down of the requirments and decide the complexity of each
Regression Testing Cycle Estimates ( Taking into account - 5 Regression cycles)
When a Regression Cycle is valid please choose valid = Yes, Else No . The Effort will be calculated on it's own.
Each proceeding Regression cycle is assumed to take half the time of the preceeding cycle.
| Regression Cycle | Valid | Effort
| Regression Cycle 2 | No | 0
| Regression Cycle 3 | No | 0
| Regression Cycle 4 | No | 0
| Regression Cycle 5 | No | 0
Sample

## 02 Summary
Note : Do not edit any colored cells, only cells in "white" can be edited
Estimates - Break Up
Estimation based on Template |  |  |  |  | Estimation based on Past data
Total Size | 51 | Complexity Point
Phase/Activity | Estimated Efforts (in Hrs) | Estimated Effort Distribution (%) |  | Stream | Testing
Requirement Analysis | 11.25 | 6.988% |  | Size (Complexity points) | 51
Test Design | 29.25 | 18.17% |  | Past productivity data | 0.19
Test Execution | 43 | 26.71% |  | Total Effort (Person hours) | 268.4211
Defect Management | 12.75 | 7.919%
Regression Testing | 43.5 | 27.02% |  | Note
Review | 2.25 | 1.398% |  | Estimate using the template and arrive at the total effort
Rework | 3 | 1.863% |  | Estimate the total effort from the past data also
Project Management | 16 | 9.938% |  | Using both, arrive at the project specific effort
Total Effort( in Person Hours) | 161 | 100% |  | In the project specific effort, identify phase/activity in scope
Distribute the project specific effort to the relavant activities
Project Specific Effort Distribution
Total project specific effort decided (person hours) | 193.2
Phase/Activity | Phase/Activity In Scope | Project Specific Effort (Hrs) | Project Specific Effort Distribution (%) | Comments for project specific effort distribution
Requirement Analysis | Yes | 11.25 | 6.988%
Test Design | Yes | 29.25 | 18.17%
Test Execution | Yes | 43 | 26.71%
Defect Management | Yes | 12.75 | 7.919%
Regression Testing | Yes | 43.5 | 27.02%
Review | Yes | 2.25 | 1.398%
Rework | Yes | 3 | 1.863%
Project Management | Yes | 16 | 9.938%
Total Effort( in Person Hours) |  | 161 | 100%
Contigency Effort |  | 32.2 | 20%
KT |  | 150
Test Data |  | 100
Other Non Testing Activities |  | 100
Leadership Time
Note on B33: Upto 20% of the total effort can be considered as Contingency, based on the project complexity

## Effort Definition
Complexity Vs. Effort Per Activity
Manual Testing
Effort by Complexity Classification (in person hours) |  |  |  |  | 2 | Simple
Activity / Complexity | Very Simple | Simple | Medium | Complex | 2 | Medium
Requirement Analysis | 0.25 | 0.5 | 1 | 2 | 1 | Complex
Test Design | 0.25 | 1 | 3 | 5
Test Execution | 1 | 1 | 4 | 8
Defect Management /Triage | 0.25 | 0.25 | 1.5 | 2
Regression Testing | 0.5 | 0.5 | 3 | 10
Review | 0 | 0.25 | 0.25 | 0.25
Rework | 0 | 0.25 | 0.25 | 0.5
Reporting/Tracking/Other Activities | 0.25 | 7 | 0.25 | 0.25
Total | 2.5 | 10.75 | 13.25 | 28
** Very Simple : Those requirments which have the test design re-useable for other lines of buisness and requires very minimal updations.
** Simple , Medium , Complex are as per the Complexity Guideline

## Complexity Guide
Complexity Guideline
Note:
| Complexity (BRD/Module/StoryCard/Req/Test Case) | UI (Field Level) validations | Functional Validations | Buisness Rule Validations |  |  | DB Validation (Number of DBs involved) | Integration Points | Others |  | UI Validation (Field Level) - No. of verification points. Ex. Presence of the field, Property of the field… Functional Validation - functionality of the module/requirement being tested. Ex. Dynamic field population, button clicks.. Business Rule Validation - functionality impact on the business flow. Ex. Assignment, DB Validation - Validation of data in the back end Intergration Points - Number of integration points tested
|  |  |  | Simple | Medium | Complex
| Complex | 70 | 35 | 4 | 4 | 4 |  | 4 | 4
| Medium | 21-69 | 11-34 | 2-3 | 2-3 | 2-3 | 0 | 3-3 | 3-3
| Simple | 20 | 10 | 1 | 1 | 1 |  | 2 | 2
Points to Note
**Only cells in Blue are editable.
** Please Change the parameter values based on the technology / platform / available knowledge resource for project being estimated
** Ensure only Numberic values are entered. The lesser than and greater than will be taken into account by the calculator .
** Ensure that Complex field entries are greater than the Simple field entries at any point in time
** User discretion can be used in defining the complexities. Hint : Further break down of the requirments and decide the complexity of each
Complexity Calculator
Note:
|  | UI (Field Level) validations | Functional Validations | Business Rule Validations |  |  | DB Validation (Number of DBs involved) | Integration Points | Others | Result | Please Enter numeric values only on the approx number of validations points for each type and the "Result" column will calcualte the complexity of the Requirment ( BRD/Module/Story Card/Test case)
|  |  |  | Simple | Medium | Complex
| Complexity calculator | 5 | 40 | [6 empty] | Complex
|  | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0
3
Complexity Point Guideline
|  | Very Simple | Simple | Medium | Complex
| Complexity Point | 1 | 3 | 5 | 8

## Verison History (hidden)
Version History
Version No | Changes Made | Author | Date
V1.0 | Initial Version | Rajini | 2011-09-22
V2.0 | Incorporated formulas into the Complexity Guide | Gopinath | 2011-10-31
V3.0 | Incorporated for protection and final touches before QMS review | Rajini | 2011-10-31
V4.0 | Incorporated the Complexity Point calculation - as per review comments from Srinivasa | Rajini | 2011-11-02
V5.0 | Modified the Complexity Guide and Effort Definition after discussion with project leads | Rajini | 2011-11-04

## Assumptions
Sl. No | Assumption

## Version History
Template Revision History
Ver. No | Ver. Date | Prepared By | Reviewed By | Approved By | Affected Section & Summary of Change
1 | 2023-10-04 | Sai Maheshwaran Rajan | Drew/Liya | Liya | All